## Sample Gantt Chart
Sample Software Implementation Gantt Chart
Task | Person Responsible | Number of Days | Week
|  |  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8
|  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
New software installation | Clinic Manager/Vendor | 4 | bar: 1 S to 1 W
Data Migration to new software | Clinic Manager/Vendor | 3 | bar: 1 T to 1 S
Training | Vendor | 14 | bar: 2 S to 3 S
CHA Training: Billing, Scheduling, Reporting | CHA/Vendor | 7 | bar: 2 S to 2 S
Practitioners: Billing, Scheduling, Reporting | Practitioners/Vendor | 7 | bar: 2 W to 3 W
Practitioners: Cllinical note taking | Practitioners/Vendor | 7 | bar: 3 S to 3 S
Testing in Clinic (ensure software is working and staff is comfortable using it) | Clinic Team | 7 | bar: 4 S to 4 S
Buffer Zone (Allow for extra time before go-live in case something delays implementation) |  | 7 | bar: 5 S to 5 S
CHA Go-Live date (CHAs will begin using new software for patient management) | CHAs | 7 | bar: 6 S to 6 S
Practitioner Go-Live date (Practitioners begin using clinical note taking feature of new software) | Practitioners | 7 | bar: 7 S to 7 S
Training refresher: Have all staff go through a training refresher (e.g. videos) to ensure they are using the software appropriately | Clinic Team | 7 | bar: 8 S to 8 S
Celebrate a successful transition with your staff! | Clinic Team | 1 | bar: 8 S

## Blank Gantt Chart
Your Clinic's Software Implementation Gantt Chart
Task | Person Responsible | Number of Days | Week
|  |  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10
|  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S